## Risks
Risk Register: Risks
[Company name]
One row per risk. The six rows are examples for a twelve person software company on AWS: replace them with your own. Score is likelihood times impact.
ID | Risk | Category | Owner | Likelihood | Impact | Score | Treatment | Control | Evidence | Residual score | Identified | Last reviewed | Next review | Notes
R-01 | An engineer leaves and keeps AWS and GitHub access, because offboarding is a Slack message | Access | CTO | 3 | 5 | 15 | Mitigate | AC-04 | Offboarding checklist, access review export
R-02 | Long lived AWS access keys sit on laptops and never rotate | Access | Platform lead | 3 | 4 | 12 | Mitigate | AC-07 | Monthly IAM credential report, keys over ninety days
R-03 | All four engineers approve and merge their own pull requests | Change | CTO | 4 | 3 | 12 | Mitigate | CM-02 | Branch protection export, sample of merged requests
R-04 | The production database snapshots nightly and nobody has restored one | Availability | Platform lead | 2 | 5 | 10 | Mitigate | BC-01 | Quarterly restore test record, with duration
R-05 | One admin role issues refunds and edits the billing record behind them | Fraud | CEO | 2 | 4 | 8 | Mitigate | FR-01 | Monthly refund report, signed and dated
R-06 | The transactional email vendor holds customer addresses and has no SOC 2 report | Vendor | Head of operations | 3 | 3 | 9 | Accept | VM-03 | Acceptance memo, vendor register entry |  |  |  |  | Accepted by the CEO, review at renewal

## Scale
Risk Register: Scale
[Company name]
Score every row on the same scale, so a 4 means the same thing in every row.
Rating | Likelihood | Impact
1 | Not expected in the next three years | Minor inconvenience, no customer effect
2 | Could happen in the next three years | Limited internal disruption
3 | Could happen in the next year | Some customers affected or a contract breached
4 | Expected in the next year | Customer data exposed, or the service down for every customer
5 | Expected within months | Severe harm to customers or the business

## How to use
Risk Register: How to use
[Company name]
1. Give every risk an ID that is never reused, one sentence saying what happens and to what, and one named owner.
2. Rate likelihood and impact from 1 to 5 using the Scale sheet. The score is calculated.
3. Choose one treatment: mitigate, transfer, avoid or accept. Looking into it further is not a treatment.
4. Point every mitigated row at a control from your control list, and say where its evidence lives.
5. An accepted risk needs a named person with authority to accept it, the date they accepted it, and a date to look again. Write that in Notes.
6. Review the whole register at least once a year, and the rows a significant change touches when it happens. Record the date in Last reviewed.
7. Evidence for the auditor: this workbook with its review dates, and the evidence each control row points to.
8. Source: free template from www.polaralabs.com/templates/risk-register (CC BY 4.0).