## Incident log
Security Incident Log: Incident log
[Company name]
One row per security event or incident, opened at triage and never deleted. The three rows are an example from Moonrake, a fictional ten person company on AWS: replace them with your own.
Incident ID | Detected on | Reported by | Detection source | Severity | Category | Systems affected | Customer data affected | Summary | Containment action | Contained at | Eradication | Recovery | Restored at | Root cause | Customer notification required | Notification sent | Post-incident review date | Owner | Status
INC-104 | 2026-02-11 | Senior engineer | Staff report | SEV3 | Unauthorized access attempt | Okta staff sign in | No | An engineer received 14 Okta push requests at night that he had not started. He denied all of them and reported it in the security channel. | Okta sessions revoked and the password reset for the account | Same day, 35 minutes after the report | Okta number challenge turned on for every staff push sign in | The engineer signed back in with the new password | Same day | The password had been reused on a third party site that was breached | No | Not required | 2026-02-17 | Chief technology officer | Closed
INC-107 | 2026-04-07 | GitHub secret scanning | Monitoring alert | SEV2 | Credential exposure | AWS production account, GitHub | No | Secret scanning flagged an AWS access key in a pull request on a private repository. The key belonged to the deployment pipeline and could write to production. | Key deactivated in AWS Identity and Access Management | Same day, 25 minutes after the alert | Key deleted, the commit removed from the branch history, and AWS CloudTrail searched for any use of the key outside the pipeline: none found | Pipeline moved to short lived credentials through GitHub OpenID Connect | Same day, 3 hours after the alert | A long lived key copied into a local test file that was committed by mistake | No | Not required | 2026-04-10 | Engineering lead | Closed
INC-112 | 2026-08-12 | Help desk vendor security team | Vendor notice | SEV1 | Vendor incident | Customer support help desk (vendor service) | Yes | The help desk vendor reported that an attacker used a stolen vendor support credential to read customer tickets over two days. Four Moonrake tickets were read. They held customer contact names and email addresses, and one held a Moonrake API token a customer had pasted. | The pasted API token and the help desk integration key revoked, and the integration paused | Same day, 2 hours after the notice | The vendor reset its support credentials and confirmed in writing that the access path was closed | New integration key issued after the written confirmation, and the integration resumed | Two days after detection | At the vendor, a support credential without multi-factor authentication. At Moonrake, the help desk kept API tokens that customers pasted into tickets | Yes | 2026-08-14, by the chief executive officer to the four customers | 2026-08-18 | Chief technology officer | Closed

## Severity scale
Security Incident Log: Severity scale
[Company name]
Set the level at triage and raise it if the facts change. Keep these levels identical to the ones in the incident response plan.
Level | Name | Trigger | Who is told | Clock
SEV1 | Critical | Customer data reached by someone who should not have it, or production down for all customers | Incident lead by phone at once, then the executive who sends customer notices | Contained the same day. The customer notice clock starts when the incident is declared
SEV2 | High | A control failed and could have exposed data, or production degraded for some customers | Incident lead within the hour | Contained the same day. Reviewed within five business days
SEV3 | Moderate | One account, device or dependency affected, and no data was reached | A ticket, picked up the next business day | Closed inside the remediation window your policy states
SEV4 | Event | A security event triaged and found not to be an incident: a scanner finding with no sign of use, failed sign ins, a phishing email nobody clicked | Nobody is woken. The row is the record of the triage | Closed at triage, or moved to the vulnerability queue

## Post-incident review
Security Incident Log: Post-incident review
[Company name]
One row per review, held within five business days of every SEV1 to SEV3 incident. An incident is closed only when its actions are.
Incident ID | Review date | Attendees | Timeline | Time to detect | Time to contain | What worked | What did not | Actions | Action owner | Due | Closed
INC-107 | 2026-04-10 | Engineering lead, chief technology officer, the engineer who committed the key | Alert 10:12, key deactivated 10:37, CloudTrail search done 11:40, pipeline on short lived credentials 13:05 | At commit, by the scanner | 25 minutes | The scanner caught the key before the pull request merged, and the runbook for a leaked key was followed as written | The pipeline still used a long lived key a year after the plan said to retire it | Add a pre-commit secret scan to every repository template; retire the last long lived AWS key | Engineering lead | 2026-04-10 | 2026-04-10
INC-112 | 2026-08-18 | Chief technology officer, chief executive officer, support lead | Vendor notice 09:05, token and key revoked 11:00, customers notified 14 August, vendor confirmation and integration resumed 14 August | Two days after the access began, by the vendor | 2 hours from the notice | The vendor register listed the help desk with its data and its contact, so the right people were reached at once | The help desk kept secrets customers pasted into tickets, and nothing redacted them | Turn on redaction of strings shaped like Moonrake API tokens in the help desk; add a line to the support signature asking customers never to send tokens | Support lead | 2026-08-18 | 2026-08-18

## How to use
Security Incident Log: How to use
[Company name]
1. Open a row in the Incident log the moment an event is triaged. Write Unknown where nothing is known yet and update the row as the response moves.
2. Set the severity from the Severity scale sheet. An event that is not an incident stays in the log at SEV4: that row is the evidence it was looked at.
3. Use the same incident ID on the ticket, the review and any customer notice.
4. Decide whether customers must be told against your contracts, your published commitments and any law that applies, and record the day the notice was sent.
5. Hold a written review within five business days of every SEV1 to SEV3 incident and record it on the Post-incident review sheet. Close the incident only when its actions are closed.
6. Never delete or rewrite a row. Add a dated note to correct one.
7. If the period had no incidents, keep the SEV4 rows and have management sign the statement of no security incidents in the Security Incident Log document.
8. Evidence for the auditor: this workbook with rows dated inside the audit period, the tickets behind them, the reviews and any customer notices. The log is read against CC7.3, CC7.4 and CC7.5.
9. Source: free template from www.polaralabs.com/templates/incident-log (CC BY 4.0).