## Findings
Vulnerability Tracker: Findings
[Company name]
One row per vulnerability found in [Company name] systems. Add a row the day a finding is confirmed and close it only with a fix date and evidence.
ID | Found on | Source | System | Finding | Severity | Due by | Owner | Status | Fixed on | Evidence link

## Response times
Vulnerability Tracker: Response times
[Company name]
The maximum time [Company name] allows between finding a vulnerability and fixing it. Due by equals Found on plus these days.
Severity | Fix within (days) | Example
Critical | 7 | Remotely exploitable flaw in a production system, or one already being exploited.
High | 30 | Serious flaw that needs some access or user action to exploit, such as an outdated library with a known exploit.
Medium | 90 | Flaw with limited impact or hard to exploit, such as a missing security header.
Low | 180 | Minor hardening item or informational finding.

## How to use
Vulnerability Tracker: How to use
[Company name]
1. Every finding gets a row, whatever its source: scanner, penetration test, dependency alert, customer or researcher report.
2. Set Severity using the scanner rating or the Response times sheet, then set "Due by" to the "Found on" date plus the days for that severity.
3. Every row has one named owner. Status moves Open > In progress > Fixed. "Fixed on" and an evidence link (the pull request, ticket or rescan result) are required to close a row.
4. "Accepted risk" is only for a finding that will not be fixed. [Policy approver role] approves it in writing, and the reason goes in the Finding column or the linked ticket. Review accepted risks every quarter.
5. Free scanners that cover most small companies
6. GitHub Dependabot: turn on Dependabot alerts and security updates in each repository (Settings > Code security). Free for all repositories. It flags vulnerable open source dependencies and opens fix pull requests.
7. Trivy: free, open source scanner for container images, file systems and infrastructure as code. Run it in the build pipeline, for example "trivy image <image>".
8. OWASP ZAP (ZAP): free, open source web application scanner. Run a baseline scan against a staging copy of the product.
9. Package manager audits: "npm audit", "pip-audit" or "bundle audit" list known vulnerable dependencies at no cost.
10. Monthly routine (first working week of each month)
11. Review open Dependabot alerts and scanner results, and add any new finding here.
12. Run the web application scan and the container scan, and save the reports.
13. Check every open row against its due date. Escalate anything overdue to [Policy approver role].
14. [Security owner role] records the review date in the Notes of the most recent row or in the monthly review record.
15. Evidence for the auditor: this tracker, the saved scan reports and the pull requests or tickets that fixed each finding.
16. Source: free template from www.polaralabs.com/templates/vulnerability-tracker (CC BY 4.0).